## Gantt Chart
ONE Development Gantt Chart
Red bars: critical tasks. Gray bars: noncritical tasks. Duration: 35 working days.
Day 1 starts at boundary 0. Bars cover every scheduled working day through the finish day.

## Schedule
ONE Task Schedule
| Duration in working days |  |  |  | 35
ID | Task | Predecessors | Days | ES | EF | LS | LF | Slack | Start offset | Critical | Noncritical
T1 | T1 Confirm ONE requirements and interfaces | None | 3 | 1 | 3 | 1 | 3 | 0 | 0 | 3 | 0
T2 | T2 Design database and audit records | T1 | 4 | 4 | 7 | 4 | 7 | 0 | 3 | 4 | 0
T3 | T3 Design employee and approval interfaces | T1 | 3 | 4 | 6 | 5 | 7 | 1 | 3 | 0 | 3
T4 | T4 Build login profile directory and dashboard shell | T2, T3 | 5 | 8 | 12 | 8 | 12 | 0 | 7 | 5 | 0
T5 | T5 Build internal attendance and payslip adapter | T2 | 4 | 8 | 11 | 9 | 12 | 1 | 7 | 0 | 4
T6 | T6 Build attendance dashboard and leave workflows | T4, T5 | 6 | 13 | 18 | 13 | 18 | 0 | 12 | 6 | 0
T7 | T7 Test increment 2 and shared request handling | T6 | 2 | 19 | 20 | 19 | 20 | 0 | 18 | 2 | 0
T8 | T8 Build expenses and payslip enquiries | T7 | 5 | 21 | 25 | 21 | 25 | 0 | 20 | 5 | 0
T9 | T9 Build IT assets and support | T7 | 5 | 21 | 25 | 21 | 25 | 0 | 20 | 5 | 0
T10 | T10 Prepare approved documents and ONEAI retrieval | T4 | 4 | 13 | 16 | 22 | 25 | 9 | 12 | 0 | 4
T11 | T11 Integrate announcements notifications and ONEAI | T8, T9, T10 | 4 | 26 | 29 | 26 | 29 | 0 | 25 | 4 | 0
T12 | T12 Run end to end and quality acceptance tests | T11 | 4 | 30 | 33 | 30 | 33 | 0 | 29 | 4 | 0
T13 | T13 Prepare demonstration deployment and documentation | T12 | 2 | 34 | 35 | 34 | 35 | 0 | 33 | 2 | 0